POCKET DEVELOPER

Build Strategy & Technical Decisions

Commercial Real Estate Site Intelligence Platform

Version 1.0  |  February 2026

Prepared by JT  |  JT Dev LLC

CONFIDENTIAL

# Table of Contents

1.  Executive Summary	3

2.  Technical Stack Decisions	4

3.  The Mobile Strategy	6

4.  Frontend Architecture	7

5.  Backend Architecture	9

6.  Database & Data Layer	11

7.  AI / ML Pipeline	13

8.  Infrastructure & DevOps	14

9.  Data Acquisition Plan	15

10.  Phased Build Plan	16

11.  Risk Register	18

12.  Cost Model	19

# 1. Executive Summary

Pocket Developer is a commercial real estate site intelligence platform that transforms raw parcel data into actionable development decisions. It replaces generic tools like LandGlide with a proprietary system that combines parcel mapping, AI-powered site analysis, data center infrastructure scoring, and a firm’s own deal history into a single, field-ready interface.

This document formalizes the technical stack, architecture decisions, mobile strategy, and phased build plan. Every decision is evaluated against three criteria: speed to DeThomas demo (Phase 1), ability to scale to multi-tenant SaaS (Phase 4), and alignment with the solo-developer build reality.

Product Scope

Phase 1: LandGlide replication — interactive parcel map, owner/zoning data, GPS field use, saved properties

Phase 2: AI site analysis — composite scoring, zoning AI chat, auto-comps, deal history RAG, feasibility briefs

Phase 3: Data center site selector — power/fiber/water/environmental scoring, tier classification, site comparison

Phase 4: Firm intelligence platform — proprietary ML model, deal pipeline CRM, white-label multi-tenancy, API layer

Anchor Client

DeThomas Investments / Swope DeThomas. They have requested a proposal. Pricing target: $18K–$22K setup + $3,500/month platform fee. The Phase 1 demo is the gate to the contract.

Key Technical Constraints

- Solo developer build (JT) — 10–15 hours/week alongside Airbus W-2 and Georgia Tech MS

- Must support both desktop dashboard and mobile field use from day one

- Heavy geospatial workload (PostGIS, vector tiles, spatial queries) is the defining technical challenge

- AI/ML pipeline must be decoupled from the frontend database for independent scaling

# 2. Technical Stack Decisions

The stack is chosen to maximize three things simultaneously: developer velocity for a solo build, production readiness for a paying client, and a clear path to multi-tenant SaaS without a rewrite. Every choice below has been pressure-tested against alternatives.

Confirmed Stack

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend | Next.js 15 (App Router) | React Server Components for data-heavy views; client components for map. Single codebase for web + mobile PWA. |
| Mobile | PWA → Capacitor | PWA for Phase 1–2 (instant deploy, no App Store). Capacitor wraps the same codebase into native iOS/Android shells for Phase 3+ when native GPS, push, offline are needed. |
| Maps | Mapbox GL JS v3 | Superior vector tile performance, custom styling for dark HUD theme, better cost model than Google Maps for tile overlays. |
| Backend API | Python FastAPI | Async, type-safe, native Pydantic validation. Hosts all scoring engines, LLM orchestration, RAG pipeline, and ML training. |
| Database | Supabase (Postgres 15) | Managed Postgres with PostGIS, pgvector, Row-Level Security, Realtime subscriptions, and built-in Auth. Single DB for all data. |
| Vector Store | pgvector (in Supabase) | No separate vector DB needed. Embeddings live alongside relational data. Simplifies joins between deal docs and parcels. |
| Auth | Supabase Auth + RLS | JWT-based, supports email/password and SSO. Row-Level Security enforces org isolation at the DB layer — critical for Phase 4 multi-tenancy. |
| AI / LLM | Claude API (Anthropic) | Primary LLM for zoning interpretation, feasibility briefs, and deal RAG. OpenAI text-embedding-3-large for embeddings (best retrieval quality at 3072 dims). |
| ML Training | XGBoost + SHAP | Gradient boosted trees for firm-specific scoring (Phase 4). Works with hundreds of samples, interpretable via SHAP. No GPU needed. |
| Hosting | Vercel + Railway | Vercel for Next.js (edge functions, ISR). Railway for FastAPI + background workers. Both scale from free tier to production. |
| Job Queue | Redis + ARQ | Async job processing for scoring, RAG ingestion, model retraining, watch alerts. ARQ is lightweight Python-native. |
| File Storage | Supabase Storage / R2 | Deal documents, generated PDFs, ML model artifacts. Supabase Storage for Phase 1–2, Cloudflare R2 for cost optimization at scale. |
| Email | Resend | Transactional email (alerts, digests, team notifications). Generous free tier, simple API. |

# 3. The Mobile Strategy

This is the most consequential architecture decision in the entire project. DeThomas developers walk sites with iPhones. The field experience must be excellent. But building and maintaining a separate native app as a solo developer is a timeline killer. The strategy is a deliberate three-stage progression.

Why Not React Native from Day One?

The original conversations considered React Native via Expo. After evaluating it against the project’s specific requirements, it’s the wrong choice at this stage for three reasons.

- Mapbox GL’s React Native bindings (@rnmapbox/maps) have a history of breaking changes, inconsistent gesture handling, and slower feature parity with the JS SDK. The web SDK (mapbox-gl-js v3) is the gold standard.

- Two codebases (Next.js + React Native) doubles every UI change. As a solo developer, this is unsustainable. Every hour spent syncing UI between web and mobile is an hour not spent on the scoring engine or RAG pipeline — the features that actually differentiate the product.

- App Store review cycles (1–7 days) kill iteration speed. During the co-development phase with DeThomas, you need to ship fixes and features same-day. A PWA deploys in seconds.

The Three-Stage Mobile Progression

| Stage | Timeline | Approach | What It Unlocks |
| --- | --- | --- | --- |
| Stage 1 | Phase 1–2 | Progressive Web App (PWA). Next.js + service worker + web app manifest. User adds to home screen from Safari/Chrome. | Full Mapbox GL JS, geolocation, offline map tile caching, instant deploys. No App Store dependency. |
| Stage 2 | Phase 3 | Capacitor Native Shell. Same Next.js codebase wrapped in Capacitor. Builds to iOS .ipa and Android .apk from one source. | Native push notifications, background GPS tracking for site visits, offline SQLite sync, biometric auth, App Store presence. |
| Stage 3 | Phase 4+ | Selective Native Modules. Keep Capacitor shell but add native Swift/Kotlin plugins for camera (site photos), AR overlay (parcel boundary visualization), and Bluetooth (field instrument pairing). | Premium native features that justify enterprise pricing. AR parcel visualization is a compelling demo moment. |

PWA Capabilities That Cover Phase 1–2

The web platform has matured substantially. The following capabilities are available in PWA mode on both iOS Safari and Android Chrome, which covers every feature needed through Phase 2:

| Capability | iOS Safari | Android Chrome |
| --- | --- | --- |
| Geolocation (GPS) | Full support | Full support |
| Add to Home Screen | Full support | Full support + install prompt |
| Offline Caching (Service Worker) | Full support | Full support |
| Camera Access | Full support | Full support |
| Push Notifications | Supported (iOS 16.4+) | Full support |
| Background Sync | Limited | Full support |
| Persistent Storage | Limited (7-day eviction) | Full support |

The iOS 7-day storage eviction for PWAs is the primary limitation. For Phase 1–2 this is manageable — parcel data is fetched live and user session tokens refresh on each visit. By Phase 3, the Capacitor shell eliminates this restriction entirely.

Capacitor vs. Alternatives

| Framework | Pros | Cons | Verdict |
| --- | --- | --- | --- |
| Capacitor | Wraps existing Next.js. One codebase. Native plugin ecosystem. No new framework to learn. | WebView performance ceiling for heavy animations (not relevant for map apps). | CHOSEN |
| React Native | True native rendering. Large ecosystem. | Separate codebase from Next.js. Mapbox RN bindings are unreliable. Doubles maintenance. | Rejected |
| Expo + Web | Cross-platform from one codebase. | Web output is not Next.js (loses SSR, ISR, API routes). Mapbox support is experimental. | Rejected |
| Flutter | Excellent performance. Good maps support. | Dart language. No code sharing with Next.js or Python backend. New ecosystem to learn. | Rejected |

# 4. Frontend Architecture

Framework: Next.js 15 with App Router

The App Router is the correct choice over Pages Router for this project. Server Components handle the data-heavy dashboard views (Phase 4 executive dashboard, pipeline Kanban) without shipping computation to the client. Client Components handle the interactive map layer where Mapbox GL JS must run in the browser.

Project Structure

pocket-developer/

app/                        # Next.js App Router

(auth)/                    # Auth group: login, register

(platform)/                # Authenticated app shell

map/                     # Phase 1: Main map view

dashboard/               # Phase 4: Executive dashboard

pipeline/                # Phase 4: Deal Kanban

alerts/                  # Phase 4: Watch alerts

settings/                # Org settings, API keys

api/                        # Next.js API routes (BFF layer)

parcel/[apn]/            # Proxies to FastAPI

score/[apn]/             # Proxies to FastAPI

components/

map/                        # MapContainer, ParcelLayer, etc.

panels/                     # ParcelPanel, ScoreTab, ZoningTab

pipeline/                   # KanbanBoard, DealCard

dashboard/                  # Charts, KPIs, heatmap

ui/                         # Shared primitives (shadcn/ui)

lib/

supabase/                   # Client + server Supabase clients

mapbox/                     # Map config, layer definitions

store/                      # Zustand stores

public/

manifest.json               # PWA manifest

sw.js                        # Service worker

State Management: Zustand

Zustand over Redux or Context for three reasons: minimal boilerplate, TypeScript-first, and it works identically in both Server and Client Components. The primary stores are:

| Store | Responsibility |
| --- | --- |
| useMapStore | Selected parcel APN, map center/zoom, active layers, base map style, comparison tray |
| useParcelStore | Current parcel data, scores cache, zoning rules, comps results |
| usePipelineStore | Deal list, active stage filters, drag state (Phase 4) |
| useAuthStore | Current user, org, role, feature flags |

UI Component Library: shadcn/ui + Tailwind CSS

shadcn/ui provides the base component primitives (Drawer, Dialog, Tabs, Command palette) built on Radix UI. Tailwind CSS handles all styling. The wireframe design system’s CSS custom properties (--brand-primary, --brand-secondary) are injected at the layout level and override Tailwind’s defaults — this is how white-labeling works in Phase 4 without a separate build per client.

Key Frontend Libraries

| Package | Version | Purpose |
| --- | --- | --- |
| mapbox-gl | ^3.x | Core map rendering engine |
| @shadcn/ui | latest | UI primitives (Drawer, Tabs, Dialog) |
| zustand | ^4.x | Client state management |
| @tanstack/react-query | ^5.x | Server state, caching, deduplication |
| recharts | ^2.x | Dashboard charts (Phase 4) |
| react-pdf | ^7.x | Client-side PDF generation for briefs |
| next-pwa | ^5.x | Service worker + manifest generation |
| @supabase/ssr | latest | Supabase client for Next.js App Router |

# 5. Backend Architecture

The backend is a Python FastAPI service that owns all business logic: scoring engines, LLM orchestration, RAG pipeline, ML training, and the external API. The Next.js frontend never talks directly to external AI services — everything routes through FastAPI. This separation is non-negotiable for three reasons: it keeps API keys server-side, it enables independent scaling of compute-heavy operations, and it means the mobile app (PWA or Capacitor) hits the same API as the web dashboard.

Service Structure

pocket-developer-api/

app/

main.py                    # FastAPI app, CORS, middleware

config.py                  # Settings via pydantic-settings

deps.py                    # Dependency injection (DB, auth)

routers/

parcels.py                 # /api/parcels/{apn}

scores.py                  # /api/scores/{apn}

zoning.py                  # /api/zoning/interpret

comps.py                   # /api/comps/{apn}

briefs.py                  # /api/briefs/{apn}

datacenter.py              # /api/datacenter/score/{apn}

deals.py                   # /api/deals (Phase 4 pipeline)

external_v1.py             # /api/v1/ (Phase 4 public API)

scoring/

engine.py                  # SiteScorer composite

zoning.py                  # ZoningScorer

access.py                  # AccessScorer (Mapbox Isochrone)

demographics.py            # DemoScorer (Census API)

market.py                  # MarketActivityScorer

infrastructure.py          # InfraScorer (Phase 2)

power.py                   # PowerScorer (Phase 3)

fiber.py                   # FiberScorer (Phase 3)

water.py                   # WaterScorer (Phase 3)

datacenter.py              # DataCenterScorer composite

ai/

zoning_interpreter.py      # LLM zoning Q&A

brief_generator.py         # Structured brief generation

comps_summarizer.py        # LLM comps narrative

rag/

ingestion.py               # Doc extraction + chunking

embeddings.py              # Embedding generation

retriever.py               # Similarity search + reranking

ml/

dataset_builder.py         # Training data from deal outcomes

firm_model.py              # XGBoost training + SHAP

predictor.py               # Inference endpoint

jobs/

watch_alerts.py            # Nightly watch area scanner

model_retrain.py           # Overnight model retraining

competitive_intel.py       # Public records scanner

webhooks/

dispatcher.py              # HMAC-signed webhook delivery

Backend-for-Frontend (BFF) Pattern

The Next.js API routes (/app/api/) act as a thin proxy layer (BFF) between the browser and FastAPI. They handle three things: attaching the Supabase JWT for user identity, adding org-scoped headers for RLS enforcement, and response caching via Next.js ISR where appropriate. The browser never calls FastAPI directly.

Key Python Dependencies

| Package | Purpose |
| --- | --- |
| fastapi + uvicorn | Async API framework + ASGI server |
| pydantic + pydantic-settings | Schema validation, structured LLM output, config management |
| sqlalchemy + asyncpg | Async Postgres ORM with PostGIS support via GeoAlchemy2 |
| anthropic | Claude API client for zoning/brief/RAG generation |
| openai | text-embedding-3-large for vector embeddings |
| xgboost + shap + scikit-learn | Firm ML model training and explainability (Phase 4) |
| arq | Redis-backed async job queue (scoring, ingestion, alerts) |
| llama-index | SemanticSplitterNodeParser for deal doc chunking |
| llama-parse | High-fidelity PDF/doc extraction for deal documents |
| httpx | Async HTTP client for Census API, Mapbox Isochrone, SOS scraper |
| playwright | Headless browser for Georgia SOS LLC lookup scraping |

# 6. Database & Data Layer

Supabase’s managed Postgres instance is the single source of truth for all data: parcels, scores, deal documents, user state, and infrastructure datasets. PostGIS handles spatial queries, pgvector handles embeddings, and Row-Level Security enforces tenant isolation. This is one database, not a microservices constellation of specialized stores.

Core Schema Groups

| Table Group | Phase | Description |
| --- | --- | --- |
| parcels | 1 | Parcel records with APN, owner, zoning, sale history, PostGIS geometry (MultiPolygon 4326) |
| zoning_rules | 2 | Structured zoning ordinance data by county/zone code: permitted uses, setbacks, height, lot coverage |
| site_scores | 2 | Cached composite + sub-scores per parcel, with org-specific weight overrides |
| deal_documents | 2 | RAG chunks with pgvector embeddings (VECTOR 3072), document metadata, org isolation |
| power_substations | 3 | HIFLD substation data: location, voltage tiers, capacity, owner |
| transmission_lines | 3 | HIFLD TX line geometries with voltage classification |
| water_systems | 3 | EPA SDWIS water system boundaries, capacity, source type |
| fema_flood_zones | 3 | FEMA NFHL flood zone polygons |
| nwi_wetlands | 3 | USFWS National Wetlands Inventory polygons |
| organizations | 4 | Multi-tenant org records: branding, settings, feature flags, plan tier |
| deals | 4 | Deal pipeline: stage lifecycle, outcome tags, ML labels, assigned users |
| deal_activities | 4 | Activity log per deal: notes, stage changes, document uploads |
| saved_parcels + collections | 1 | User bookmarks organized into named project folders with team sharing |

PostGIS Spatial Indexing Strategy

Every geometry column gets a GiST index. Spatial queries (nearest substations, comps within radius, flood zone intersection) are the most performance-critical operations in the system. The query pattern is always ST_DWithin for distance filtering (uses the index) followed by ST_Distance for precise ordering.

CREATE INDEX idx_parcels_geom ON parcels USING gist(geom);

CREATE INDEX idx_substations_geom ON power_substations USING gist(geom);

CREATE INDEX idx_flood_geom ON fema_flood_zones USING gist(geom);

CREATE INDEX idx_deals_embedding ON deal_documents USING ivfflat(embedding vector_cosine_ops);

Row-Level Security Model

RLS is enabled on every user-facing table starting in Phase 1, not added later. The policy pattern is consistent: users see data belonging to their org_id. This is enforced at the Postgres level, not in application code, which means a bug in the API can never leak cross-tenant data.

ALTER TABLE deals ENABLE ROW LEVEL SECURITY;

CREATE POLICY org_isolation ON deals

USING (org_id = (SELECT org_id FROM users WHERE id = auth.uid()));

# 7. AI / ML Pipeline

LLM Integration Architecture

All LLM calls route through the FastAPI backend, never from the client. The integration follows a structured output pattern: every prompt includes a response schema (via Pydantic models) and the LLM output is validated before being returned to the frontend. This eliminates hallucination risk in structured fields like score breakdowns and zoning rule citations.

| Feature | Model | Input | Output |
| --- | --- | --- | --- |
| Zoning Interpreter | Claude Sonnet 4 | Parcel + zoning rules + user query | Plain-language zoning answer with ordinance citations |
| Comps Summary | Claude Haiku 4 | Top 5 comp records | 2-sentence value range narrative |
| Feasibility Brief | Claude Sonnet 4 | All scores + comps + RAG context | Structured SiteBrief Pydantic model (8 sections) |
| Deal RAG | Claude Sonnet 4 | Retrieved chunks + parcel context | Historical context narrative with deal references |
| Competitive Intel | Claude Haiku 4 | Public records batch | Structured alert summaries |

RAG Pipeline

Deal document ingestion follows a four-stage pipeline: extraction (LlamaParse for mixed PDF/doc content), semantic chunking (LlamaIndex SemanticSplitterNodeParser to keep proforma sections coherent), embedding (OpenAI text-embedding-3-large at 3072 dimensions), and storage in pgvector. Retrieval uses cosine similarity search with a minimum threshold of 0.72 to avoid surfacing irrelevant matches.

ML Training Pipeline (Phase 4)

The firm-specific scoring model is an XGBoost regressor trained on deal outcomes (executed, passed, lost) with site features as inputs. SHAP TreeExplainer generates per-prediction feature attributions that surface in the UI as natural-language explanations. The model retrains overnight whenever a new deal outcome is recorded, with cross-validation R² tracked as the quality metric. A drift detection alert fires if R² drops below 0.6 on the most recent 20% holdout.

# 8. Infrastructure & DevOps

Deployment Architecture

| Service | Host | Configuration |
| --- | --- | --- |
| Next.js Frontend | Vercel | Edge runtime, ISR for dashboard pages, Preview deployments per PR |
| FastAPI Backend | Railway | Docker container, auto-deploy from main branch, 512MB–2GB RAM scaling |
| Redis (ARQ) | Railway | Managed Redis instance, same private network as FastAPI |
| Postgres + PostGIS | Supabase | Managed, automatic backups, connection pooling via Supavisor |
| File Storage | Supabase Storage | Deal documents, generated PDFs, model artifacts |
| Domain / DNS | Cloudflare | SSL, DDoS protection, edge caching for static assets |

CI/CD Pipeline

GitHub Actions handles the full pipeline. On push to main: lint (ESLint + Ruff), type check (TypeScript + mypy), run tests (Vitest + pytest), build, deploy. Vercel auto-deploys the frontend. Railway auto-deploys the backend. Database migrations run via Supabase CLI in the pipeline before deployment.

Environment Strategy

| Environment | Purpose | Data |
| --- | --- | --- |
| local | Development on your machine. Docker Compose for Postgres + Redis. | Gwinnett County extract only. Seed data. |
| staging | Preview builds for DeThomas review. Vercel preview URLs. | Full county extracts. Anonymized deal data. |
| production | Live platform. Custom domain (app.pocketdeveloper.com). | Full data. Real deal documents. Live auth. |

# 9. Data Acquisition Plan

Every feature in the platform depends on external data. The table below maps each data source to its cost, refresh cadence, and the phase that first requires it. All federal datasets are public domain and free. The only paid acquisition is the Regrid parcel extract.

| Dataset | Source | Cost | Phase | Refresh |
| --- | --- | --- | --- | --- |
| Parcel Boundaries + Owner | Regrid | $600–$900 | Phase 1 | Quarterly re-pull |
| Zoning Overlays | County GIS portals | Free | Phase 1 | Annual |
| Census Demographics | Census Bureau ACS | Free | Phase 2 | Annual (5-yr estimates) |
| Power Substations | HIFLD / EIA | Free | Phase 3 | Semi-annual |
| Transmission Lines | HIFLD / EIA | Free | Phase 3 | Semi-annual |
| Utility Territories | FERC / HIFLD | Free | Phase 3 | Annual |
| Fiber Providers | FCC BDC | Free | Phase 3 | Semi-annual |
| Flood Zones | FEMA NFHL | Free | Phase 3 | As updated by FEMA |
| Wetlands | USFWS NWI | Free | Phase 3 | Annual |
| Brownfield Sites | EPA FRS/ACRES | Free | Phase 3 | Quarterly |
| Water Systems | EPA SDWIS | Free | Phase 3 | Annual |
| Deal Documents | Client (DeThomas) | Free | Phase 2 | Continuous ingestion |

# 10. Phased Build Plan

The build is structured so that each phase delivers a usable, demonstrable product increment. Phase 1 is the DeThomas demo. Phase 2 closes the contract. Phase 3 opens a new market. Phase 4 builds the SaaS business.

Phase 1: LandGlide Replication (6–8 weeks)

DELIVERABLE: Demo-ready parcel intelligence map

| Feature | Effort | Tech Focus |
| --- | --- | --- |
| Interactive Parcel Map | High | Mapbox GL JS + Regrid vector tiles via Tippecanoe |
| Parcel Detail Panel | Medium | Supabase query + Shadcn Drawer/Panel component |
| GPS + Address Search | Low | navigator.geolocation + Mapbox Search Box API v2 |
| LLC Owner Lookup | Medium | Playwright headless scraper → GA SOS → Supabase cache |
| Saved Properties + Collections | Medium | Supabase Auth + saved_parcels/collections tables |
| Map Layer Toggles | Low | Mapbox style switching + setLayoutProperty visibility |

Phase 2: AI Site Analysis (8–10 weeks)

DELIVERABLE: Closes the DeThomas contract

| Feature | Effort | Tech Focus |
| --- | --- | --- |
| AI Site Score Card | High | FastAPI scoring engine + Census API + Mapbox Isochrone |
| Zoning Intelligence Engine | High | Structured rules DB + Claude API for interpretation |
| Auto-Comps Analysis | Medium | PostGIS spatial query + Claude narrative summary |
| Deal History RAG | High | LlamaParse + LlamaIndex + pgvector + Claude retrieval |
| AI Feasibility Brief + PDF | Medium | Pydantic structured output + react-pdf / Puppeteer |

Phase 3: Data Center Site Selector (8–10 weeks)

DELIVERABLE: New market vertical unlocked

| Feature | Effort | Tech Focus |
| --- | --- | --- |
| Power Infrastructure Scoring | High | HIFLD data + PostGIS spatial + PowerScorer module |
| Fiber & Connectivity Scoring | High | FCC BDC + Overpass API + FiberScorer module |
| Water & Cooling Analysis | Medium | EPA SDWIS + WaterScorer + cooling tech flag logic |
| Environmental Risk Layer | Medium | FEMA + NWI + EPA FRS + binary disqualifier flags |
| DC Composite Score + Tier | Medium | Weighted composite + Uptime Institute tier mapping |
| Site Comparison Mode | Medium | Zustand comparison store + full-screen comparison UI |
| Capacitor Native Shell | Medium | Wrap PWA in Capacitor for iOS/Android App Store builds |

Phase 4: Firm Intelligence Platform (10–14 weeks)

DELIVERABLE: SaaS business with real lock-in

| Feature | Effort | Tech Focus |
| --- | --- | --- |
| Firm ML Model (XGBoost + SHAP) | Very High | Training pipeline + SHAP explainer + overnight retrain |
| Deal Pipeline CRM (Kanban) | High | Zustand drag state + Supabase Realtime + outcome tags |
| Multi-Tenant White Label | High | RLS policies + branding JSONB + CSS custom properties |
| Team Collaboration + RBAC | Medium | org_memberships + role enum + Supabase Realtime |
| Executive Dashboard | Medium | Recharts + materialized views + model performance card |
| External API + Webhooks | Medium | FastAPI versioned router + HMAC webhook dispatcher |
| Site Watch Alerts | Medium | ARQ scheduled jobs + spatial watch queries + Resend email |

# 11. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Solo developer burnout / stall | High | Critical | Get DeThomas LOI before Phase 1 complete. External accountability + revenue commitment changes motivation dynamics. Consider part-time contractor at Phase 2. |
| Regrid data quality gaps | Medium | High | Start with Gwinnett County extract to validate coverage and field quality before purchasing additional counties. Have a fallback to county assessor direct feeds. |
| Mapbox GL JS performance on large tile sets | Low | High | Use Tippecanoe to pre-generate optimized vector tiles at multiple zoom levels. Limit max-zoom parcel rendering to z13+. Test on low-end mobile devices early. |
| Supabase PostGIS query performance at scale | Medium | Medium | Proper GiST indexing from day one. Use EXPLAIN ANALYZE on every spatial query during development. Connection pooling via Supavisor handles concurrent users. |
| iOS PWA storage eviction (7-day rule) | Medium | Low | Acceptable for Phase 1–2 (data fetched live). Capacitor native shell in Phase 3 eliminates this entirely. |
| LLM API cost overrun in production | Low | Medium | Cache scoring results aggressively. Use Haiku for simple summaries, Sonnet only for complex interpretation. Budget $200–$400/month at moderate usage. |
| Georgia SOS scraper breaks | High | Low | SOS website changes will break the Playwright scraper. Build with defensive parsing + error handling. This is a nice-to-have, not a core dependency. |
| DeThomas budget lower than proposal | Medium | High | Have the Phase 1 only pilot ready: $8,500 setup + $1,500/month for 90 days with credit toward full engagement. Never discount the full proposal — descope instead. |

# 12. Cost Model

Year 1 Infrastructure Costs (Solo Build)

| Item | Monthly | Annual | Phase |
| --- | --- | --- | --- |
| Supabase Pro | $25 | $300 | 1 |
| Vercel Pro | $20 | $240 | 1 |
| Railway (FastAPI + Redis) | $25–$40 | $360–$480 | 2 |
| Mapbox (beyond free tier) | $0–$200 | $0–$2,400 | 1 (free during dev) |
| Regrid County Extracts (5 counties) | — | $600–$900 | 1 (one-time) |
| LLM API (Claude + OpenAI embeddings) | $50–$400 | $600–$4,800 | 2 |
| LlamaParse (doc ingestion) | — | $15–$40 | 2 (one-time) |
| Resend (email) | $0–$20 | $0–$240 | 4 |
| Domain + Cloudflare | $15/yr | $15 | 1 |
| TOTAL INFRASTRUCTURE | $135–$705 | $2,130–$9,415 |  |

Legal & Go-to-Market (Year 1)

| Item | Cost |
| --- | --- |
| LLC Formation (Georgia) | $100–$200 |
| SaaS/Services Agreement (attorney) | $1,500–$3,000 |
| Privacy Policy + ToS | $150–$300 |
| E&O / Tech Liability Insurance | $800–$1,500 |
| TOTAL LEGAL + GTM | $2,550–$5,000 |

Total Year 1 Out-of-Pocket (Solo Build)

$5,000 – $14,000 total  |  Your time is the primary investment

At the proposed pricing of $20K setup + $3,500/month, DeThomas covers all Year 1 costs in the first month and generates $42K+ in annual recurring revenue. The financial model works at any reasonable scale of infrastructure spend.

END OF DOCUMENT

Pocket Developer  |  Build Strategy v1.0  |  February 2026